## Participation
Strategic goal: | Strengthen women's participation and leadership in all areas related to peace and security
Goal | Measure | Measure description | Indicator | Default indicator value | Target indicator value | Measure implementation period | Authority | Cooperating authorities
Provide relevant data on gender issues enabling further strategic planning, | Commission a study on the perception of security in the population of the Czech Republic. | Commissioning of a study on security perception in the population of the Czech Republic. The study should answer the following questions and topics: What is perceived as security and how is perceived the role of NATO, the UN and the EU in ensuring security? It will be possible to gender-desegregate the results of the study. | # studies | 0 | 1 | 1 January 2021 - 31 December 2024 | Foreign Ministry | Defence Ministry, Interior Ministry
| Conduct an internal survey to identify the motivations and barriers of younger generations in relation to work in the Czech Army, Police of the Czech republic and participation in foreign missions, based on which recommendations will be drawn up to support women's and girls' interest in working in the Czech Army, Police of the Czech Republic and sending women to foreign missions. | Conducting of an internal gender-desegregated survey on the motivations and barriers of younger generations in relation to work in the Czech Army and Police of the Czech Republic as well as the participation in foreign missions, with a focus on preferred positions. Based on the survey, recommendations will be drawn up to support women's and girls' interest in working in the Czech Army and Police of the Czech Republic and sending women to foreign missions. | # internal surveys # set of recommendations | 0 0 | 2 2 | 1 January 2021 - 31 December2023 1 January 2024 - 31 December 2025 | Defence Ministry, Interior Ministry, Ministry of Justice
| Conduct an internal survey on parents´ motivation to return to service or work in the Police of the Czech Republic after parental leave, based on which a personnel strategy will be updated and material including examples of good practice will be created. | Conducting of an internal survey on women´s motivation to return to service or work in the Police of the Czech Republic after parental leave, based on which a personnel strategy of the Czech Police will be created / updated with emphasis on motivational elements to encourage women to return after parental leave and a set of recommendations including examples of good practice will be drawn up. | # internal surveys # set of recommendations | 0 0 | 1 1 | 1 January 2021 - 31 December 2024 | Interior Ministry
| Conduct a final independent expert audit of the second NAP. | Elaboration of an independent expert audit of the second NAP conducted in the final stage of the action plan´s implementation. The results of the expert audit will form one of the bases for the elaboration of the third NAP for the period 2026-2030. | # final audits | 0 | 1 | 1 January 2024 - 31 July 2025 | Foreign Ministry | Government Office, Defence Ministry, Interior Ministry, Ministry of Justice, Non-Governmental Organizations, Academia
Monitor the representation of women in foreign missions. | Conduct an internal survey mapping the currently set preconditions for deployment on foreign missions. | Conducting of an internal survey mapping the currently set system of preconditions and possible barriers to deployment on foreign missions. | # internal surveys | 0 | 1 | 1 January 2021 - 31 December 2023 | Interior Ministry, Ministry of Justice
| Conduct an internal survey mapping the motivations of women civil servants of the Ministry of the Interior, members of the Police of the Czech Republic and employees of the Ministry of Justice who participated in a foreign mission or are preparing for it. | Conducting of an internal survey mapping the motivations of women civil servants of the Ministry of the Interior, members of the Czech Parliament and employees of the Ministry of Justice who participated in a foreign mission or are preparing for it. | # internal surveys | 0 | 1 | 1 January 2021 - 31 December 2023 | Interior Ministry
| Create a set of recommendations to support the motivation of women civil servants of the Ministry of the Interior, members of the Police of the Czech Republic and employees of the Ministry of Justice to participate in foreign missions. | Creation of a set of recommendations to support the motivation of women civil servants of the Ministry of the Interior and members of the Czech Parliament to participate in foreign missions based on the internal survey mapping the system of preconditions and barriers. | # set of recommendations | 0 | 1 | 1 January 2024 - 31 December 2025 | Interior Ministry, Ministry of Justice
Monitor balanced representation of women and men in the executive positions in the departments of the Ministry of Foreign Affairs, the Ministry of the Interior and the Ministry of Defence | Keep and regularly evaluate anonymised gender-desegregated statistics on the selection procedures for the executive positions and their results, namely at the Ministry of Foreign Affairs, the Ministry of the Interior and the Ministry of Defence. | The Ministry of Foreign Affairs, the Ministry of the Interior and the Ministry of Defence will keep and regularly evaluate on an annual basis anonymised gender-desegregated statistics on the selection procedures for the executive positions and their results. | % of the selection procedures for the executive positions and their results per year, for which anonymised, gender-desegregated data will be collected and regularly evaluated | 0% | 100% | 1 January 2021 - 31 December 2025 | Foreign Ministry, Interior Ministry, Defence Ministry
| Seek gender-balanced selection committees for the executive positions. | Seek to secure gender-balanced selection committees for the executive positions in order to ensure that the committees are represented by both men and women. | % of the selection procedures for the executive positions annually, where both men and women will be represented | - | 75% | 1 January 2021 - 31 December 2025 | Foreign Ministry, Interior Ministry, Defence Ministry
Monitor the representation of men and women in the army and police forces. | Monitor and consistently evaluate the percentages of female and male students, their success rates at admission examinations at each police and military school. | Monitoring and consistent evaluation of the percentages of female and male students and their success rates at admission examinations at each police and military school. | # evaluation annually | 1 | 1 (5) | 1 January 2021 - 31 December 2025 | Interior Ministry, Defence Ministry
| Monitor and consistently evaluate the success rates of women and men in recruitment procedures to the Czech Parliament and the Czech Armed Forces. | Monitoring and consistent evaluation of the success rates of women and men in recruitment procedures to the Czech Parliament and the Czech Armed Forces. | # evaluation annually | 2 | 2 (10) | 1 January 2021 - 31 December 2025 | Interior Ministry, Defence Ministry
Secure participation of the non-profit sector and the academic community in formulating the Czech Republic's activities in the field of peace and security. | On an annual basis, hold meetings with female human rights activists, journalists and women-led NGOs at selected Czech embassies. | On an annual basis, Czech Embassies will hold a special meeting with female human rights activists, journalists and women-led NGOs. | # annually held meetings | 0 | 6 (30) | 1 January 2021 - 31 December 2025 | Foreign Ministry
| Increase the percentage of NGOs and the academic sector representatives in the total number of members of the MFA working group on the WPS Agenda. | Increase the percentage of NGOs and the academic sector representatives in the total number of members of the MFA working group on the WPS Agenda. | % NGOs and the academia representatives in the total number of members of the MFA working group on the WPS Agenda | - | 30% | 1 January 2021 - 31 December 2025 | Foreign Ministry | Government Office, NGOs, academic sector
| Arrange at least two meetings of the Inter-Ministerial working group on the WPS Agenda in each calendar year. | Arranging at least two meetings of the Inter-Ministerial working group on the WPS Agenda in each calendar year under the leadership of the national coordinator of the WPS Agenda. | # meetings of the working group on the WPS Agenda per year | 2 | 2 (10) | 1 January 2021 - 31 December 2025 | Foreign Ministry | Government Office, Defence Ministry, Interior Ministry, Ministry of Justice, NGOs, academic sector
| Establish the post of the elected Vice-Chair of the Inter-Ministerial working group on the WPS Agenda. | Establishment of the post of elected Vice-Chair of the Inter-Ministerial working group on the WPS Agenda from among NGOs / academia. | # Vice-Chairs of the Inter-Ministerial working group on the WPS Agenda | 0 | 1 | 1 January 2021 - 31 December 2025 | Foreign Ministry
| Secure the representation of NGOs and the academic sector in the Czech delegation at the meeting of the Commission on the Status of Women. | Active initiative and support of the participation of NGOs and the academic sector in the annual meetings of the Commission on the Status of Women on the part of the administrators of the Commission on the Status of Women. | % of NGOs and academia representatives in the Czech delegation at the meeting of the Commission on the Status of Women per year | 30% | 30% | 1 January 2021 - 31 December 2025 | Foreign Ministry, Government Office
| Organize a workshop / seminar with NGOs and civil society and business representatives on WPS with a focus on a specific region. | Annual organization of a workshop / seminar with NGOs and civil society and business representatives on WPS with a focus on a specific region. The aim is to pass on and share WPS experience with partners from abroad. | # meetings | 0 | 1 | 1 January 2021 - 31 December 2025 | Foreign Ministry
* Foreign mission means a stay abroad longer than 7 days, carried out within the framework of fulfilling the principles of the WPS Agenda

## Gender Mainstreaming
Strategic goal: | Systematically strengthen gender mainstreaming in all areas related to peace and security
Goal | Measure | Measure description | Indicator | Default indicator value | Target indicator value | Measure implementation period | Authority | Cooperating authorities
Provide education and training on the WPS Agenda | Include the topic of gender equality and WPS in training courses for teachers of primary prevention of risky behaviour, organized by the University of Defence. | Inclusion of the topic of gender equality and WPS in the training courses for teachers of primary prevention of risky behaviour, organized by the University of Defence. | % of teachers of the prevention of risky behaviour participating in courses including "gender equality and WPS" topic, organized by the University of Defence per year | - | 100% | 1 January 2022 - 31 December 2025 | Defence Ministry
| Prepare an introductory e-learning course on gender equality, available for use by personnel of the Ministry of Foreign Affairs, the Ministry of the Interior and the Ministry of Defence. | Preparation of an introductory e-learning course on gender equality, available for use by personnel of the Ministry of Foreign Affairs, the Ministry of the Interior and the Ministry of Defence. | # e-learning course on gender equality | 0 | 1 | 1 January 2021 - 31 december 2022 | Government Office | Foreign Ministry, Interior Ministry, Defence Ministry
| Prepare an introductory e-learning course on WPS, intended for new WPS Agenda employees of the key departments and other interested men and women from the Ministry of Foreign Affairs, the Ministry of the Interior, the Ministry of Defence. | Preparation of an introductory e-learning course on WPS, intended for new WPS Agenda employees of the key departments and other interested men and women from the Ministry of Foreign Affairs, the Ministry of the Interior, the Ministry of Defence. | # e-learning course on WPS | 0 | 1 | 1 January 2021 - 31 December 2021 | Foreign Ministry
| Conduct an annual training on a specific topic within the WPS Agenda open to applicants from among the state administration, NGOs and academia. | Conducting of an annual training on WPS open to applicants from the state administration, NGOs and academia. | # trainings on WPS per year | 0 | 1 | 1 January 2021 - 31 December 2025 | Foreign Ministry, Government Office
| Ensure participation of all gender / WPS focal points at the Ministry of Foreign Affairs, the Ministry of Defence, the Ministry of the Interior and the Government Office in professional training on gender issues. | Ensure participation of all gender / WPS focal points at the Ministry of Foreign Affairs, the Ministry of Defence, the Ministry of the Interior and the Government Office in a professional training on gender issues no later than 12 months after taking office. (e-learning course on gender equality prepared by the Government Office, e-learning course on WPS prepared by the Foreign Ministry or another training) | % gender a WPS focal points at the Foreign Ministry, Defence Ministry, Interior Ministry and Government Office who participated in a professional training no later than 12 months after taking office | - | 100% | 1 January 2021 - 31 December 2025 | Foreign Ministry, Interior Ministry, Defence Ministry, Government Office
| Ensure active participation of professional representatives of the Government Office, the Ministry of Foreign Affairs, the Ministry of Defence, the Ministry of the Interior, police officers and soldiers in international educational events and conferences on WPS issues. | Support of active participation of professional representatives of the Government Office, the Ministry of Foreign Affairs, the Ministry of Defence, the Ministry of the Interior, police officers and soldiers in international educational events and conferences on WPS issues. | # participants from the Foreign Ministry, Defence Ministry, Interior Ministry and Government Office in international educational events and conferences on WPS issues in a calendar year # evaluation reports from participation in international educational events and conferences on WPS issues in a calendar year | - | 3 (15) 3 (15) | 1 January 2021 - 31 December 2025 | Foreign Ministry, Interior Ministry, Defence Ministry, Government Office
Ensure support for UN agencies in implementing WPS agenda | Regularly contribute to the UN Women budget on an annual basis. | Regular annual contributions to the UN Women budget. | the annual value of the contribution to the budget of UN Women | 400,000 CZK | 500,000 CZK | 1 January 2021 - 31 December 2025 | Foreign Ministry
| Actively run for membership in the Commission on the Status of Women for the years 2023-2027. | Ensuring the active candidature of the Czech Republic for membership in the Commission on the Status of Women for the years 2023-2027. | # candidatures of the Czech Republic for membership in the Commission on the Status of Women | 1 | 1 | 1 January 2021 - 30 April 2022 | Foreign Ministry | Government Office
| Actively participate in the meetings of the Group of Friends of the WPS Agenda in New York and Geneva. | Ensuring active participation in the official meetings of the Group of Friends of the WPS Agenda in New York and Geneva. | % of meetings of the Group of Friends of the WPS Agenda attended by representatives of the Czech Republic in the given year | - | 75% | 1 January 2021 - 31 December 2025 | Foreign Ministry
Collaborate and share information between partner countries on WPS issues | Ensure the active participation of the Czech Republic in the meetings of the EU working group on the WPS Agenda. | Ensuring the active participation of the Czech Republic in the meetings of the EU working group on the WPS Agenda. | % of meetings of the EU working group on the WPS Agenda attended by the Czech Republic representatives in the given year | 75% | 75% | 1 January 2021 - 31 December 2025 | Foreign Ministry
| Consult partner countries on WPS or gender issues. | Appropriate incorporation of the WPS Agenda and gender equality to bilateral consultations with partner countries, including good practice discussions. | # bilateral consultations on the WPS Agenda or gender equality in the annual agenda | - | 10 (50) | 1 January 2021 - 31 December 2025 | Foreign Ministry, Defence Ministry
| Identify and subsequently implement a suitable project focused on the WPS Agenda implementation in cooperation with a foreign partner. | Identification and subsequent implementation of a suitable project focused on the WPS Agenda implementation abroad in cooperation with a suitable foreign partner. | # suitable projects | 1 | 2 | 1 January 2021 - 31 December 2025 | Defence Ministry, Foreign Ministry
Spread awareness about the WPS Agenda and gender equality issues in general | Organize annual conferences on gender equality in foreign policy and on WPS. | Organization of an annual conference on gender equality in foreign policy and on WPS. | # conferences on gender equality in foreign policy and on WPS in the given year | 1 | 1 (5) | 1 January 2021 - 31 December 2025 | Foreign Ministry | Government Office,NGOs, academic sector
| Create a website on WPS. | Creation of a publicly accessible website on WPS within the Foreign Ministry website, where the minutes from the meetings of the Inter-Ministerial working group on the WPS Agenda will be posted, a list of group members will be published and links to relevant resolutions and basic information on upcoming events will be shared. | # websites on WPS | 0 | 1 | 1 January 2021 - 31 December 2021 | Foreign Ministry | Defence Ministry, Interior Ministry, Government Office, Ministry of Justice, NGOs, academic sector
| Anchor the gender equality / WPS agenda in the activities of the departments concerned in the organizational regulations of the Ministry of Foreign Affairs, the Ministry of the Interior and the Ministry of Defence. | Explicit anchoring of the gender equality / WPS agenda in the activities of the departments concerned in the organizational regulations of the Ministry of Foreign Affairs, the Ministry of the Interior, the Ministry of Defence. | # personnel members of key departments of the Ministry of Foreign Affairs, the Ministry of the Interior and the Ministry of Defence with gender equality / WPS anchored in their agendas | - | 11 | 1 January 2021 - 31 December 2021 | Foreign Ministry, Interior Ministry, Defence Ministry
* in the case of the Ministry of Foreign Affairs, these would be the departments which are members of working groups on gender and the Inter-Ministerial working group on WPS

## Prevention and Protection
Strategic goal: | Actively participate in strengthening conflict prevention through the promotion of women's rights and gender equality
Goal | Measure | Measure description | Indicator | Default indicator value | Target indicator value | Measure implementation period | Authority | Cooperating authorities
Provide relevant data to incorporate gender issues into peace and security agendas | Include a gender analysis in reports on development in conflict countries and priority ODA countries at least once a year. | Include a gender analysis in reports on development in conflict countries and priority ODA countries at least once a year. | % of embassies in conflict countries and priority ODA countries which shared at least 1 gender analysis of the situation in the country per year |  | 100% | 1 January 2021 - 31 December 2025 | Foreign Ministry
Strengthen active prevention of all forms of gender-based violence and support victims of domestic, sexual and gender-based violence | Inform migrants in an appropriate way about support services concerning prevention, assistance, care and recovery from domestic, sexual and gender-based violence. | Inclusion of information about support services concerning prevention, assistance, care and recovery from domestic, sexual and gender-based violence in information courses and information materials for migrants. | % of persons (who completed the Adaptation-Integration Course in the given year) who received information on domestic, sexual and gender-based violence | - | 100% | 1 January 2022 - 31 December 2025 | Interior Ministry | NGOs
| Create an educational module to present legal and cultural differences relating to sexual and gender-based violence, with a focus on a sensitive approach and differences in perception of this issue in other cultures and countries. | Creation of an educational module to present legal and cultural differences relating to sexual and gender-based violence with a focus on a sensitive approach and differences in perception of this issue in other cultures and countries (e.g. module Sexual and gender-based violence and foreigner women). The module will be intended for civil servants, personnel of the Ministry of the Interior and members of the Czech Parliament who, as part of their service / work, come into contact with foreigners who are victims of domestic or gender-based violence in the Czech Republic . The module will be part of the Lifelong Learning Course at the Police Academy. | # educational modules | 0 | 1 | 1 January 2021 - 31 December 2022 | Interior Ministry | NGOs
Benefit from the membership of the Czech Republic in the UN Human Rights Council to support its preventive role | Actively run for membership in the UN Human Rights Council for the years 2025-2027. | Ensuring active candidature of the Czech Republic for a membership in the UN Human Rights Council for the years 2025-2027. | # candidatures of the Czech Republic for a membership in the UN Human Rights Council | 1 | 1 | 1 January 2021 - 31 October 2024 | Foreign Ministry
| As part of the Universal Periodic Review, ensure that gender issues are reflected in national recommendations. | Ensuring that gender issues are reflected in national recommendations to relevant countries as part of the Universal Periodic Review. | % of gender-related recommendations to relevant countries in the given year |  | 100% | 1 January 2021 - 31 December 2025 | Foreign Ministry
| As part of the Czech Republic's activity in the UN Human Rights Council, actively support the participation of women and civil society in resolutions. | As part of the Czech Republic's activity in the UN Human Rights Council, actively support the participation of women and civil society in resolutions and national initiatives of the Czech Republic. | # co - sponsored resolutions in the given year | 2 | 2 (10) | 1 January 2021 - 31 December 2021 | Foreign Ministry
| As part of the Czech Republic's activity in the UN Human Rights Council, actively support the participation of women and civil society in the Czech Republic's national initiatives. | As part of the Czech Republic's activity in the UN Human Rights Council, actively support the participation of women and civil society in resolutions and national initiatives of the Czech Republic. | # accompanying events organized in the given year | 0 | 1 (5) | 1 January 2021 - 31 December 2025 | Foreign Ministry

## Assistance and Recovery
Strategic goal: | Provide and support adequate development and transformation cooperation and humanitarian assistance geared towards the needs of women and girls
Goal | Measure | Measure description | Indicator | Default indicator value | Target indicator value | Measure implementation period | Authority | Cooperating authorities
Develop methods and tools to reflect the gender dimension of needs in ODA and humanitarian aid | Create and apply methodological guidelines for gender mainstreaming in cross-cutting themes in all phases of ODA and humanitarian aid project cycle. | Development of methodological guidelines for gender mainstreaming in cross-cutting themes in all phases of the project cycle, leading to gender mainstreaming, including women's empowerment and the safeguarding agenda, throughout ODA and humanitarian aid. | # existing methodologies with clearly defined criteria to assess whether a project is gender sensitive or transformational % gender sensitive or transformational ODA projects | 0 - | 1 60% | 1 January 2021 - 31 December 2022 1 January 2023 - 31 December 2025 | Foreign Ministry | Council for Development Cooperation, The Czech Development Agency
| Introduce a Code of Conduct for entities implementing ODA and humanitarian aid projects of the Czech Republic. | Introduction of a Code of Conduct based on the recommendations of the UN Global Compact and the OECD (DAC Recommendation on Ending Sexual Exploitation, Abuse, and Harassment in Development Co-operation and Humanitarian Assistance), the principles of which will be binding for all entities implementing development cooperation and humanitarian aid projects of the Czech Republic. | % of entities bound by the principles contained in the Code of Conduct in the given year | 0 | 100% | 31 December 2021 - 31 December 2025 | Foreign Ministry | Council for Development Cooperation
| Increase the share of ODA and humanitarian aid projects with local implementers, where gender equality is cross-sectionally taken into account. | Increasing the share of ODA and humanitarian aid projects with local implementers, where gender equality will be cross-sectionally taken into account, including active involvement of women in all phases of project implementation. | % of projects with a local implementer in the given year, where gender equality is taken into account |  | 25% | 1 January 2021 - 31 December 2025 | Foreign Ministry | The Czech Development Agency
Develop methods and tools ensuring the gender dimension reflection of needs in transformational cooperation | Incorporate ​​gender equality into the forms for submitting transformation cooperation projects. | Cross-sectional incorporation of gender issues in forms for the submission of transformation cooperation projects, including support for the involvement of women in all phases of project implementation. | % of forms with the incorporated topic of gender equality in a given year | 0 | 100% | 1 January 2021 - 31 December 2021 | Foreign Ministry
| Incorporate gender equality into project evaluation. | Taking into account the gender dimension of a project in the selection of transformation cooperation projects. | % of transformation cooperation projects, where the gender dimension of the project was assessed during the selection in a given year | 0 | 100% | 1 January 2021 - 31 December 2021 | Foreign Ministry
Implement projects which take the WPS Agenda significantly into account | As part of the Government's "Programme of Activities for Supporting Source and Transit Countries of Migration in Africa in the period 2020 - 2022", implement at least one activity within the 3rd pillar of "Good governance, social development" in 2021 and 2022, where the WPS Agenda will be significantly taken into account . | As part of the Government's "Programme of Activities for Supporting Source and Transit Countries of Migration in Africa in the period 2020 - 2022", at least one activity will be implemented within the 3rd pillar of "Good governance, social development" in 2021 and 2022 , where the WPS Agenda will be significantly taken into account . The activities under the measure will be implemented in selected countries of the Sahel, West Africa or the Horn of Africa in accordance with the Programme. The priority countries for cooperation in these regions are Mali and Ethiopia. | # activities | 0 | 1 | 1 January 2021 - 31 December 2022 | Foreign Ministry